## Sheet1
Bhavika Korat
Mohammed Saad
Gantt Chart | [16 empty] | Adam Ruppert
Brandon Trussell
Zach McKellar
Tasks | 2019 |  |  | 2020 | [8 empty] | 2021 | [11 empty] | 2022
| Oct | Nov | Dec | Jan | Feb | March | April | May | June | July | Aug | Sept | Jan | Feb | March | April | May | June | July | Aug | Sept | Oct | Nov | Dec | Jan | Feb | March
Understand two systems | bar: 2019 Oct to 2019 Nov
Check Visa application(F1,B1,H1B1) | bar: 2019 Nov to 2019 Dec
List effected system(credit card) | bar: 2020 Jan to 2020 Feb
Id field requirements | bar: 2020 Feb to 2020 April
Gain government approval | bar: 2019 Nov to 2020 July
Negotiate terms with countries | bar: 2020 Aug to 2021 Feb
Start building system | bar: 2021 March to 2021 Aug
Digitalize form | bar: 2021 June to 2021 Sept
Find cloud computing system | bar: 2021 Aug to 2021 Oct
Test the sytem | bar: 2021 Sept to 2021 Nov
Roll out (Bridge System) | bar: 2021 Dec to 2022 March
| October |  |  | November
Team Deliverables- Leader of Assignment | 2019 Oct: 2nd Week; 2019 Nov: 3rd Week; 2019 Dec: 4th Week; 2020 Jan: 1st Week; 2020 Feb: 2nd Week; 2020 March: 3rd Week; 2020 April: 4th Week
Assignment#1 - Mohammed | 2019 Oct: 8th; 2019 Nov: :Business Model (Adam & Mohammed): CII system breakdown (Zach & Brandon) :Gant Chart (Bhavika, Adam, Mohammed)
Assignment#2- Adam | 2019 Nov: 17th; 2019 Dec: :Functional and Non-functional Requirements (Mohammed, Adam & Bhavika) :Actors and use cases (Adam, Mohammed & Brandon) :create a glossary of actor and use case (Zach, Bhavika, Brandon )
Assignment#3- Bhavika | 2019 Dec: 31th; 2020 Jan: :Detailed Use Case Specifications (Adam, Mohammed):extended use case diagram (Zach, Brandon): Adjusted case Points (Bhavika, Adam) :effort per use case point (Zach, Mohammed)
Assignment#4- Brandon | 2020 March: 14th; 2020 April: : List Candidate classes(Mohammed, Brandon), atttributes and operations(Zach, Bhavika) :Preliminary Class Diagram(Bhavika, Adam) :Extended Class Diagram (Brandon, Mohammed)
Assignment #5- Zach | 2020 April: 26th; 2020 May: :SWL and DBMS showing relationships (Zach, Adam) :Interface Design(Brandon,Bhavika):Search Queries (Mohammed, Bhavika)